## Sheet1
GRAPHIC DESIGNER: PENG
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH
1 | TEXT | POSTER TAJWID 1 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
2 | TEXT | POSTER TAJWID 2 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
3 | TEXT | POSTER TAJWID 3 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
4 | TEXT | POSTER TAJWID 4 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
5 | TEXT | POSTER TAJWID 5 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
6 | TEXT | POSTER TAJWID 6 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
7 | TEXT | POSTER TAJWID 7 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
8 | TEXT | POSTER TAJWID 8 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
9 | TEXT | POSTER JAWI 1 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
10 | TEXT | POSTER JAWI 2 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
11 | TEXT | POSTER JAWI 3 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
12 | TEXT | POSTER JAWI 4 |  | POSTER | ASRUL |  | 0% | PENDING APPROVAL
GRAPHIC DESIGNER: JA'A
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH
1 | ILUS | GHOST 3 | KOMIK ANA MUSLIM | KOMIK | SYU | 12 | 50% | PENDING APPROVAL | 2023-09-12 | 2023-10-06
2 | ILUS | ALYA | KOMIK ALYAA DAN BABY ADAM | KOMIK | SYU | 80 | 50% | NOT YET PROPOSED |  | 2023-10-13
3
4
5
6
7
8
GRAPHIC DESIGNER: AFIQ
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH
1 | TEXT | CLAP 1,2,3… CHOIR DIVA | DIVA VOGS | NOVEL | HADA | 128 | 100% | APPROVED | 2023-09-15 | 2023-10-06
2 | TEXT | SERANGAN PUTERI SALJU | KOO KOO WEH | KOMIK | SYU | 80 | 100% | APPROVED | 2023-09-01 | 2023-09-15
3 | COVER | SERANGAN PUTERI SALJU | KOO KOO WEH | KOMIK | SYU |  | 100% | APPROVED | 2023-09-29 | 2023-10-04
4 | TEXT | SATRIA JUNIOR | HADIS AL FALAH | NOVEL | SYU | 80 | 100% | PENDING APPROVAL | 2023-10-04 | 2023-10-16
5 | TEXT | TIPS LENGKAP SCORE A+ MURID CEMERLANG | GEG GENIUS | EDUKOMIK | SYU | 80 | 100% | APPROVED | 2023-09-04 | 2023-09-27
6
7
8
GRAPHIC DESIGNER: SYAKIRIN
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH
1 | COVER | SATRIA JUNIOR | SIRI HADIS AL FALAH | NOVEL | SYU |  | 100% | PENDING APPROVAL | 2023-10-02 | 2023-10-13
2 | ILUS | GHOST 3 | KOMIK ANA MUSLIM | KOMIK | SYU | 8 | 30% |  | 2023-09-18 | 2023-10-20
3
4
5
6
7
8
GRAPHIC DESIGNER: HAZIQ
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH
1 | COVER | CLAP 1,2,3… CHOIR DIVA | DIVA VOGS | NOVEL | HADA |  | 100% | APPROVED | 2023-08-29 | 2023-09-29
2 | COVER | TIPS LENGKAP SCORE A+ MURID CEMERLANG | GENG GENIUS | EDUKOMIK | SYU |  | 100% | APPROVED | 2023-09-11 | 2023-09-29
3 | ILUS | GHOST 3 | KOMIK ANA MUSLIM | KOMIK | SYU | 8 | 30% |  | 2023-09-12 | 2023-10-06
4
5
6
7
8
GRAPHIC DESIGNER: FREELANCE
NO | TYPE | TITLE | SIRI | CATEGORY | EDITOR | PAGES # | ILLUSTRATION | TEXT/TITLE | START DATE | TARGET FINISH | FREELANCER
1 | TEXT | PERIBAHASA | NOT YET PROPOSED | NOVEL | HADA | 128 | 100% | APPROVED | 2023-09-04 | 2023-10-06 | ZARIS
2
3
4
5
6
7